## Gantt Chart
| lanslide Triggering System |  |  |  | 0%
Final Assignment
| Pham Thai Quang Nguyen |  | 2024-03-19
[11 empty] | 12 | [6 empty] | 13 | [6 empty] | 14 | [6 empty] | 15 | [6 empty] | 16 | [6 empty] | 17 | [6 empty] | 18 | [6 empty] | 19 | [6 empty] | 20 | [6 empty] | 21 | [6 empty] | 22 | [6 empty] | 23 | [6 empty] | 24 | [6 empty] | 25 | [6 empty] | 26 | [6 empty] | 27 | [6 empty] | 28 | [6 empty] | 29 | [6 empty] | 30 | [6 empty] | 31 | [6 empty] | 32 | [6 empty] | 33 | [6 empty] | 34 | [6 empty] | 35 | [6 empty] | 36 | [6 empty] | 37
WBS | Task Names | Resource Names | Start | Duration | Finish | % Complete | Calendar days | Days Completed | Days Remaining | 2024-03-17 | [14 empty] | 2024-04-01 | [29 empty] | 2024-05-01 | [30 empty] | 2024-06-01 | [29 empty] | 2024-07-01 | [30 empty] | 2024-08-01 | [30 empty] | 2024-09-01
|  |  | 2024-03-17 | 32 | 2024-04-30 | 0% | 45 | time axis 2024-03-17 to 2024-09-13
| Data warehouse construction | PostgreSQL | 2024-03-17 | 9 | 2024-03-28 | 0% | 12 | 0 | 20 | bar: 2024-03-17 to 2024-04-27
| Database schema design |  | 2024-03-17 | 5 | 2024-03-21 |  | 5 | 0 | 5
| normalization |  |  |  |  | 0% | 5 | 0 | 5
| Writing DDL script |  | 2024-03-17 | 10 | 2024-03-28 | 0% | 12 | 0 | 10
Updating Triggering
Milestone 1
| Collecting pipeline | Apache Airflow | 2024-03-23 | 7 | 2024-04-02 | 0% | 11 | 0 | 2
| Sources ingestion task | Python | 2024-03-23 | 2 | 2024-03-25 |  | 3 | 0 | 2
| download excel/csv files | Python |  |  |  | 0%
| extracting and preprocessing | Numpy & Pandas |  |  |  | 0%
| Parsing landslide event data | Python | 2024-03-25 | 5 | 2024-03-29 |  | 5 | 0 | 5
| import to PostgreSQL | Python |  |  |  | 0%
| push coordinates value | Python |  |  |  | 0% | bar: 2024-03-17 to 2024-04-27
| Weather data collecting | Python | 2024-03-27 | 5 | 2024-04-02 |  | 7 | 0 | 5
| pull Coordinates value | Python |  |  |  | 0%
| call REST API requests | Python |  |  |  | 0%
| import to PostgreSQL | Python |  |  |  | 0%
Milestone 2
| Data mining | Apache Airflow | 2024-04-03 | 16 | 2024-04-24 | 0% | 22 | 0 | 10
| Statistical Analysis | Apache Spark | 2024-04-03 | 10 | 2024-04-16 |  | 14 | 0 | 10
| Descriptive Analysis | Apache Spark |  |  |  | 0%
| Inferential Analysis | Apache Spark |  |  |  | 0%
| Causal Analysis | Apache Spark |  |  |  | 0%
| Visualization | Nginx Webserver | 2024-04-17 | 6 | 2024-04-24 |  | 8 | 0 | 6
| Chart & Graphs | ChartJS |  |  |  | 0%
| Geo Map |  |  |  |  | 0%
Milestone 3
| Training model | Mlflow | 2024-04-25 | 2 | 2024-04-26 | 0% | 2 | 0 | 2
| Load data | Apache Spark | 2024-04-25 | 2 | 2024-04-26 |  | 2 | 0 | 2
| normalization | Apache Spark |  |  |  | 0%
| standardization | Apache Spark |  |  |  | 0%
| choosing model | Mlflow
| Training | Mlflow | 2024-04-26 | 1 | 2024-04-26 |  | 1 | 0 | 1
| tuning hyper parameter | Mlflow |  |  |  | 0%
| monitoring | Mlflow |  |  |  | 0%
Milestone 4
| Triggering | Mlflow | 2024-04-25 | 4 | 2024-04-30 | 0% | 6 | 0 | 2
| Edge Device | Raspberry Pi 3 | 2024-04-25 | 2 | 2024-04-26 |  | 2 | 0 | 2
| GPS location | GPS module |  |  |  | 0%
| Publish to MQTT broker | AWS IoT Core |  |  |  | 0%
| Scheduling | Cron job |  |  |  | 0%
| Inference | Python | 2024-04-26 | 2 | 2024-04-29 |  | 4 | 0 | 2
| Subcribe to MQTT broker | Python |  |  |  | 0%
| call REST API requests | Python |  |  |  | 0%
| parse to model | Python |  |  |  | 0%
| Visualization | Python | 2024-04-30 | 1 | 2024-04-30 |  | 1 | 0 | 1
| Geo Map | Nginx Webserver |  |  |  | 0%
Alert mechanism
Milestone 5
Author: Fernando Ribeiro <pinguim.ribeiro@gmail.com>
How To Use
INSERT LINES:
Insert the required number of lines: click the line number and drag down
From the template, copy the required section or just one line
INPUT DATA:
WBS: to itemize the WBS copy and past the required level from the template
Enter a Task and Resource Names
Enter a [Start] date and a [Duration] (working days); The Due date is calculated and the task bar shows the task's duration on calendar.
Or: Enter a [Start] and [Due] dates; The [Duration] (working days) is calculated and the task bar shows the task's duration on calendar.
Enter a percentage in the [% Complete box]; the task bar shows a progress bar to indicate what percentage of the task is complete.
Milestone: If you enter a start date without an end date, a milestone marker is displayed on the bar chart.
In Categories tasks (level 1) Start, Due, Duration and Percentage Complete values are calculated; however they can be overwritten.
Holidays
2014-01-01
2014-03-04
2014-04-18
2014-04-20
2014-04-25
2014-05-01
2014-06-10
2014-08-15
2014-12-08
2014-12-25